## Gantt Chart
GANTT CHART TEMPLATE | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE |  | Group 3 College Enrollment
Date |  | 2024-10-07
Members |  | Anthony Kungo, Connor McMilan, Chen Li, Andrew Tang
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DAYS WORKED ON | PCT OF TASK COMPLETE | INITIATION | [14 empty] | PHASE ONE | [19 empty] | PHASE TWO | [19 empty] | TBD | [14 empty] | TBD
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15 |  |  |  |  | WEEK 16 |  |  |  |  | WEEK 17
[7 empty] | 8/19/24-8/23/24 |  |  |  |  | 8/26/24-8/30/24 |  |  |  |  | 9/2/24-9/6/24 |  |  |  |  | 9/9/24-9/13/24 |  |  |  |  | 9/16/24-9/20/24 |  |  |  |  | 9/23/24-9/27/24 |  |  |  |  | 9/30/24-10/4/24 |  |  |  |  | 10/7/24-10/11/24 |  |  |  |  | 10/14/24-10/18/24 |  |  |  |  | 10/21/24-10/25/24 |  |  |  |  | 10/28/24-11/1/24 |  |  |  |  | 11/4/24-11/8/24 |  |  |  |  | 11/11/24-11/15/24 |  |  |  |  | 11/18/24-11/22/24 |  |  |  |  | 11/25/24-11/29/24 |  |  |  |  | 12/2/24-12/6/24 |  |  |  |  | 12/9/24-12/13/24
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
0 | Initiation
0.1 | Presentation Slides | All | 2024-08-19 | 2024-09-04 | 6 | 100% | bar: 8/26/24-8/30/24 W to 9/2/24-9/6/24 W
1 | Phase 1: Requirements
1.1 | SRS Document | All | 2024-09-05 | 2024-09-30 | 18 | 100% | bar: 9/9/24-9/13/24 M to 9/30/24-10/4/24 W
1.2 | Meeting Minutes | All |  |  | 3 | 100% | bar: 9/30/24-10/4/24 M to 9/30/24-10/4/24 W
1.3 | Github Repo | All |  |  | 1 | 100% | bar: 9/30/24-10/4/24 W
1.4 | Presentation Slides | All |  |  | 4 | 100% | bar: 9/23/24-9/27/24 W to 9/30/24-10/4/24 M
2 | Phase 2
2.1 | Design (more deliverables TBD) | All | 2024-10-02 | 2024-10-30 | 0 | 0%
3 | Phase 3 (TBD)
4 | Phase 4 (TBD)
5 | Phase 5 (TBD)